## Hazard Flow Chart
Preliminary Hazard
List (PHL)
Hazard Reports
Hazard Verification
Tracking Log
Assign Hazard Report Numbers to Each Identified Hazard
Identify Potential
Vehicle Hazards
Identify Hazard Group
Identify Hazard Category (Catastrophic or Critcal)
Identify System Component Phase or Event Affected (Ground Processing, Launch/Ascent, On-Orbit)
Reference Applicable Safety Documents
Create Description of Hazard
Identify Hazard Causes
Create Safety Verification Methods
Identify Initial Hazard Assessment Code (RAC) Rating
Record Verification Artifacts and Verfication Method Disposition
Record Estimated and Actual Close Dates
Identify Hazard Controls
Identify Final RAC Rating
Flowchart shows process of hazards identification, cataloging, verification, tracking, and documentation.

## Hazard Report Format
HR NUMBER: |  |  | INITIAL RAC:
FINAL RAC:
SUBSYSTEM: |  |  | HAZARD GROUP: |  |  | DATE:
HAZARD TITLE: |  |  | HAZARD CATEGORY:
Catastrophic [ ] Critical [ ]
APPLICABLE SAFETY REQUIREMENTS:
DESCRIPTION OF HAZARD:
HAZARD CAUSES:
1
2
3
HAZARD CONTROLS:
1.1
2.1
3.1
SAFETY VERIFICATION METHODS:
1.1.1
2.1.1
3.1.1
STATUS OF VERIFICATIONS:
Hazard Report Number | HCSV | Hazard Controls and Verification |  | Status | Remarks
HR-# | 1.1.1
HR-# | 2.1.1
HR-# | 3.1.1
Sample Hazards Report

## Hazard Tracking Sheet
Hazard Report Number | HR-01 | HR-02 | HR-03 | HR-04
Name | Failure of Vehicle Primary/Secondary Structure | Inadvertent Release or Leakage of Propellant through a Mechanical Leak Path | Heat Pipe Rupture/Burst/Leakage | Structural Failure of Mechanical Ground Support Equipment
Owner | E. Maiden | P. Diano | P. Diano | D. Murray
Status | Closed | Closed | Closed | Closed
Approval Date | 2020-03-12 | 2020-02-09 | 2020-02-09 | 2020-02-09
Revision
Effectivity | Life of the Program | Life of program | Life of program | Life of program
Brief Hazard Description | Evaluates the risk of vehicle primary/secondary structure failure | Evaluates the risk of possible propellant lead | Evaluates the risk of heat pipe failure | Evaluates the risk of GSE failure
Risk Initial Severity | 3 | 3 | 3 | 3
Risk Initial Probability | C | C | C | C
Risk Final Severity | 1 | 1 | 1 | 1
Risk Final Probability | E | E | E | E
System/Subsystem/ Component Hazard Analysis Summary | Structrual loading, fatigue/corrosion, mfgr or assembly error assessed. | Valve, electrcial, or inadvertant command causes assessed. | Design strength, material compatibility, and mfgr and QA assessed. | Design strength, fatigue/corrosion, material selection, mfgr/assembly error, use and human factors assessed.
Statement of Acceptable Level of Risk | Meets SSPP acceptable level of risk of medium or less, per XXX.XX | Meets SSPP acceptable level of risk of medium or less, per XXX.XX | Meets SSPP acceptable level of risk of medium or less, per XXX.XX | Meets SSPP acceptable level of risk of medium or less, per XXX.XX
Severity and Likelihood Justification
Fault Tolerance Statement | System contains fault tolerance design requirements per AFSPCMAN 91-710[T] Volume 3. | System contains fault tolerance design requirements per AFSPCMAN 91-710[T] Volume 3. | System contains fault tolerance design requirements per AFSPCMAN 91-710[T] Volume 3. | System contains fault tolerance design requirements per AFSPCMAN 91-710[T] Volume 3.
Number of Causes | 4 | 3 | 3 | 5
Number of Controls | 13 | 7 | 5 | 9
Number of Verificaitons | 16 | 13 | 6 | 9
Open Verifications | 0 | 0 | 0 | 0
Record of Relevant Engineering Changes | 0 | 0 | 0 | 0
Requirement(s) Reference | AFSPCMAN 91-710V3, para xxxx.x | AFSPCMAN 91-710V3, para xxxx.x | AFSPCMAN 91-710V3, para xxxx.x | AFSPCMAN 91-710V3, para xxxx.x
Subcontractor Risk Data (as applicable) | N/A | N/A | N/A | N/A
Numerical Probability Assessment (if performed) | N/A | N/A | N/A | N/A
Preliminary Hazard Analysis Results (if performed) | N/A | N/A | N/A | N/A

## Hazard Reports
Hazard Report Number | Hazard Title
HR-01 | Failure of Vehicle Primary/Secondary Structure
HR-02 | Inadvertent Release or Leakage of Propellant through a Mechanical Leak Path
HR-03 | Heat Pipe Rupture/Burst/Leakage
HR-04 | Structural Failure of Mechanical Ground Support Equipment
Sample hazard report tracking matrix.

## HazRpt Summary
Hazard Report # | System Component Phase or Event |  |  | Hazard Report Title & Hazard Causes | IRAC | FRAC | Latest ECD | Status | % Complete
| Ground Processing | Launch/Ascent | On-Orbit
HR-01 | X |  |  | Failure of Vehicle Primary/Secondary Structure | Serious | Med
1. Excessive structural loading
2. Fatigue / Corrosion
3. Manufacturing and/or assembly error
4. Defective material
HR-02 | X |  |  | Inadvertent Release or Leakage of Propellant through a Mechanical Leak Path | Serious | Med
1. Mechanical Valve Failure
2. Electrical Failure
3. Inadvertent Commanding
HR-03 | X |  |  | Heat Pipe Rupture/Burst/Leakage | Serious | Med
1. Inadequate design strength
2. Heat pipe material incompatibility
3. Improper manufacturing and/or assembly workmanship
HR-04 | X |  |  | Structural Failure of Mechanical Ground Support Equipment | Serious | Med
1. Inadequate design strength
2. Fatigue/corrosion
3. Defective or Improper material selection
4. Manufacturing Error / Improper Assembly
5. Improper Use / Human Error
Total
HR-01 | 0%
HR-02 | 0%
HR-03 | 0%
HR-04 | 0%
Sample hazard report summary.